## Deliverables
Date | Column1 | Column2 | Column3 | Column4 | Column5 | Column6
| TL1 | TL2 | TL3 | TL4 | TL5 | TL6
2025-02-25
2025-02-27
2025-02-25 |  | 2025-02-25

## Budget
Cost Analysis
SN | Member Name | Role | Estimated Hours | Hourly Rate ($) | Estimated Cost ($) | Actual Hours | Total Cost ($) | Variance | Comments
1 | Shruti Debnath | IT Manager | 55 | 16 | 880
2 | Pratik Rauniyar | Software Architect | 60 | 18 | 1080
3 | Dristanta Silwal | Software Architect | 65 | 18 | 1170
4 | Kushal Khadka | QA Manager | 40 | 16 | 640
5 | Sikha Chaudary | Project Manager | 30 | 20 | 600
6 | Pramil Shrestha | AI Specialist | 35 | 17 | 595
7 | Prabesh Tamang | Version Control Manager | 40 | 17 | 680
| Total |  | 325 |  | 5645

## Gantt
Status Color
Completed
Working Currently
Planned
SN | Feature Breakdown | Estimated Time (weeks) | Prereq | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
Shruti Debnath
1 | Rough UI Design | 1 | N/A | Completed
2 | Gathering assests | 1 | N/A | Completed
3 | Main Menu (game-lobby, ShopScene) design | 2 | 1,2 | Completed
4 | Scripts writting | 2 | 3 | Completed
5 | New Buttons & Button Update | 1 | 2,3 | Working Currently
6 | Adding tracking bars on the Game screen | 2 | 2,3 | Working Currently
7 | Game End Scene | 2 | 6 | Planned
8 | Final Touch UP | 1 | 5,6,7 | Planned
9 | Testing and Debugging | 1 | 8 | Planned
10 | Documentation | 1 | 9 | Planned
Pratik Rauniyar
1 | Player development | 1 | N/A | Completed
2 | Actions(Player) | 1 | 1 | Working Currently
3 | Game Mechanics(logic and development) | 2 | 2 | Working Currently
4 | Game plots | 2 | 3 | Working Currently
5 | logic for game win/loose | 1 | 2, 3 | Planned
6 | logic for player and enemy reposne | 2 | 3, 4 | Planned
7 | Testing and debugging | 1 | 6 | Planned
8 | Documentation | 1 | 7 | Planned
Dristanta Silwal
1 | AI state machine Design | 2 | N/A | Completed
2 | Enemy attribute randomization | 1 | 1 | Working Currently
3 | Difficulty adjustment logic | 2 | 2 | Working Currently
4 | Enemy behavior programming | 4 | 1 | Planned
5 | Defeat and cleanup logic | 2 | 3, 4 | Planned
6 | Animation | 2 | 5 | Planned
7 | Testing and debugging | 1 | 6 | Planned
8 | Documentation | 1 | 7 | Planned
Kushal Khada
1 | Attack Enemy | 1 | N/A | Working Currently
2 | Pick up weapon | 1 | 1 | Working Currently
3 | Activates special power | 2 | 2 | Planned
4 | Takes Damages | 1 | 2 | Planned
5 | Knocked out | 1 | 3 | Planned
6 | Documentation | 1 | 4 | Planned
Sikha Chaudhary
1 | collectables placed(treasure) | 1 | N/A | Completed
2 | collectables to be placed(gems, poison) | 1 | 1 | Working Currently
3 | collectables hide/show logic | 1 | 2 | Planned
4 | collectables animation | 2 | 3 | Planned
5 | Testing and debugging | 1 | 4 | Planned
6 | Documentation | 1 | 5 | Planned
Pramil Shrestha
1 | Enter Lobby | 1 | N/A | Working Currently
2 | Manage Coins | 1 | 1 | Working Currently
3 | View Inventory | 1 | 2 | Planned
4 | Select Characters | 2 | 3 | Planned
5 | Equip Weapons | 1 | 4 | Planned
6 | Documentation | 1 | 5 | Planned
Prabesh Tamang
1 | Background stort concept development | 1 | N/A | Completed
2 | Story refinement and integration | 2 | 1 | Completed
3 | Story Testing and feedback | 1 | 1 | Completed
4 | Final Story Implementation | 1 | 2 | Completed
5 | Audio Assets Collection | 1 | 3 | Working Currently
6 | Music and Sound Design | 2 | 4 | Working Currently
7 | Sound Integration and testing | 2 | 5 | Planned
8 | Final Sounds Adjustments | 1 | 6 | Planned
9 | Bug Fixing and optimization | 1 | 7 | Planned

## estimated schedule
Schedule Work
SN | Member Name | Task Description | Estimated Hours | Actual Hours | Status | Comments
1 | Shruti Debnath | Rough UI Design | 1 | N/A | Completed
2 | Shruti Debnath | Gathering Assets | 1 | N/A | Completed
3 | Shruti Debnath | Main Menu (game-lobby, ShopScene) Design | 2 | 1 | Completed
4 | Shruti Debnath | Scripts Writing | 2 | 3 | Completed
5 | Shruti Debnath | New Buttons & Button Update | 1 | 2 | Working Currently | Implementing new UI features
6 | Shruti Debnath | Adding Tracking Bars on Game Screen | 2 | 2 | Working Currently | In progress, needs completion
7 | Shruti Debnath | Game End Scene | 2 | N/A | Planned | Scheduled for next phase
8 | Shruti Debnath | Final Touch Up | 1 | N/A | Planned | Scheduled after all features complete
9 | Shruti Debnath | Testing and Debugging | 1 | N/A | Planned | After final touch-up
10 | Shruti Debnath | Documentation | 1 | N/A | Planned | Pending completion of features
11 | Pratik Rauniyar | Player Development | 1 | N/A | Completed
12 | Pratik Rauniyar | Actions (Player) | 1 | 1 | Working Currently | Implementing player actions
13 | Pratik Rauniyar | Game Mechanics (logic and development) | 2 | 2 | Working Currently | In progress
14 | Pratik Rauniyar | Game Plots | 2 | 3 | Working Currently | In progress
15 | Pratik Rauniyar | Logic for Game Win/Lose | 1 | N/A | Planned | Scheduled for next phase
16 | Pratik Rauniyar | Logic for Player and Enemy Response | 2 | N/A | Planned | Scheduled after current tasks
17 | Pratik Rauniyar | Testing and Debugging | 1 | N/A | Planned | After completion of game mechanics
18 | Pratik Rauniyar | Documentation | 1 | N/A | Planned | Pending completion of tasks
19 | Dristanta Silwal | AI State Machine Design | 2 | N/A | Completed
20 | Dristanta Silwal | Enemy Attribute Randomization | 1 | 1 | Working Currently | In progress
21 | Dristanta Silwal | Difficulty Adjustment Logic | 2 | 2 | Working Currently | In progress
22 | Dristanta Silwal | Enemy Behavior Programming | 4 | N/A | Planned | Scheduled for next phase
23 | Dristanta Silwal | Defeat and Cleanup Logic | 2 | N/A | Planned | Scheduled after behavior programming
24 | Dristanta Silwal | Animation | 2 | N/A | Planned | Scheduled after other tasks
25 | Dristanta Silwal | Testing and Debugging | 1 | N/A | Planned | After completion of enemy behavior
26 | Dristanta Silwal | Documentation | 1 | N/A | Planned | Pending completion of tasks
27 | Kushal Khadka | Attack Enemy | 1 | N/A | Working Currently | Implementing enemy attack logic
28 | Kushal Khadka | Pick Up Weapon | 1 | 1 | Working Currently | In progress
29 | Kushal Khadka | Activates Special Power | 2 | N/A | Planned | Scheduled after current tasks
30 | Kushal Khadka | Takes Damage | 1 | N/A | Planned | Scheduled after attack implementation
31 | Kushal Khadka | Knocked Out | 1 | N/A | Planned | Scheduled after taking damage logic
32 | Kushal Khadka | Documentation | 1 | N/A | Planned | Pending completion of tasks
33 | Sikha Chaudhary | Collectables Placed (treasure) | 1 | N/A | Completed
34 | Sikha Chaudhary | Collectables to be Placed (gems, poison) | 1 | 1 | Working Currently | In progress
35 | Sikha Chaudhary | Collectables Hide/Show Logic | 1 | N/A | Planned | Scheduled after placing collectables
36 | Sikha Chaudhary | Collectables Animation | 2 | N/A | Planned | Scheduled after logic implementation
37 | Sikha Chaudhary | Testing and Debugging | 1 | N/A | Planned | After completion of animations
38 | Sikha Chaudhary | Documentation | 1 | N/A | Planned | Pending completion of tasks
39 | Pramil Shrestha | Enter Lobby | 1 | N/A | Working Currently | In progress
40 | Pramil Shrestha | Manage Coins | 1 | 1 | Working Currently | In progress
41 | Pramil Shrestha | View Inventory | 1 | N/A | Planned | Scheduled after managing coins
42 | Pramil Shrestha | Select Characters | 2 | N/A | Planned | Scheduled after inventory
43 | Pramil Shrestha | Equip Weapons | 1 | N/A | Planned | Scheduled after character selection
44 | Pramil Shrestha | Documentation | 1 | N/A | Planned | Pending completion of tasks
45 | Prabesh Tamang | Background Story Concept Development | 1 | N/A | Completed
46 | Prabesh Tamang | Story Refinement and Integration | 2 | N/A | Completed
47 | Prabesh Tamang | Story Testing and Feedback | 1 | N/A | Completed
48 | Prabesh Tamang | Final Story Implementation | 1 | 1 | Completed
49 | Prabesh Tamang | Audio Assets Collection | 1 | 1 | Working Currently | In progress
50 | Prabesh Tamang | Music and Sound Design | 2 | N/A | Working Currently | In progress
51 | Prabesh Tamang | Sound Integration and Testing | 2 | N/A | Planned | Scheduled after music design
52 | Prabesh Tamang | Final Sounds Adjustments | 1 | N/A | Planned | Scheduled after sound integration
53 | Prabesh Tamang | Bug Fixing and Optimization | 1 | N/A | Planned | Scheduled for final touches